## Server-Instance Level
SQL Server 2016 → 2022 Migration — Source-to-Target Mapping
Sheet 1 of 2 · Server / Instance level · one row per SQL Server instance
HOW TO USE: Fill one row per instance. Enter Source and Target values in the white cells. ‘Match’ columns are formulas — do not type in them (green = MATCH, red = REVIEW). Amber COLLATION band = must match or you hit collation conflicts. Row 6 is a worked EXAMPLE — overwrite or delete it. Target standards: Cost Threshold = 50, Tgt OS = Windows Server 2025.
Source Server\Instance | Target Server\Instance | Role / Function | AG Role (Primary/Sync Sec/Async DR/Standalone) | Src Edition | Tgt Edition | Edition Match | Src Product Version (e.g. 13.0.xxxx / 2016) | Tgt Product Version (e.g. 16.0.xxxx / 2022) | Src CU Level | Tgt CU Level | Src Instance Collation | Tgt Instance Collation | Collation Match | Src MAXDOP | Tgt MAXDOP | Src Cost Threshold | Tgt Cost Threshold (=50) | Src Max Mem (MB) | Tgt Max Mem (MB) | Src Min Mem (MB) | Tgt Min Mem (MB) | Src Trace Flags | Tgt Trace Flags | Notable non-default sp_configure | Src OS | Tgt OS (WS2025) | Src Cores / RAM | Tgt Cores / RAM | Service Account (gMSA?) | SPNs Registered | Migration Date | Status | Signed Off (DBA / PM) | Notes
SQL-PROD-01\MSSQLSERVER | SQL-PROD-01-N\MSSQLSERVER | Primary Production DB | Primary | Enterprise | Enterprise | MATCH | 13.0.6300 (SQL 2016 SP3) | 16.0.4165 (SQL 2022) | SP3-GDR | CU14 | SQL_Latin1_General_CP1_CI_AS | SQL_Latin1_General_CP1_CI_AS | MATCH | 4 | 8 | 5 | 50 | 57344 | 116736 | 0 | 0 | 1117,1118 | 3226 (1117/1118 now default) | optimize for ad hoc = 1 | Windows Server 2012 R2 | Windows Server 2025 | 8 vCPU / 64 GB | 16 vCPU / 128 GB | DOMAIN\gMSA_sql01$ (gMSA) | Y | TBC | Not Started |  | Highest priority — schedule window

## Database Level
SQL Server 2016 → 2022 Migration — Source-to-Target Mapping
Sheet 2 of 2 · Database level · one row per user database
HOW TO USE: Fill one row per database. ‘Collation Match’ is a formula — do not type in it. DB collation can differ from the instance collation, so capture it per database. Compat level is staged: deploy at 130, validate, then raise to 160 (do NOT jump to 160 on cutover day). Row 6 is a worked EXAMPLE — overwrite or delete it.
Source Instance | Database Name | Owner (target = dbo?) | Src DB Collation | Tgt DB Collation | Collation Match | Src Compat Level | Tgt Compat @ Cutover (130) | Final Compat Level (160) | Recovery Model | Src Data Size (MB) | Src Log Size (MB) | PAGE_VERIFY (=CHECKSUM) | Query Store Enabled | TDE Enabled | CLR | FILESTREAM | Full-Text | Service Broker | Repl/LogShip/ Mirroring | Src DBCC CHECKDB (date) | Tgt DBCC CHECKDB (date) | Restore NORECOVERY | Orphans Resolved | Rowcount/ Checksum OK | Cutover Date | Status | Notes
SQL-PROD-01\MSSQLSERVER | AppDB_Sales | dbo | SQL_Latin1_General_CP1_CI_AS | SQL_Latin1_General_CP1_CI_AS | MATCH | 130 | 130 | 160 | FULL | 42000 | 8000 | CHECKSUM | Y | N | N | N | Y | N | None | clean 01/07/26 |  | N | N | N | TBC | Not Started | Full-text catalog — validate post-restore